## DSA Tracker
Day | Phase | Pattern / Topic | Target Problems / Exercises | Time Target | Difficulty | Status (Completed) | Time Taken (min) | Notes / Gotchas
1 | Phase 1: Foundations | Two Pointers | Two Sum II, Valid Palindrome | 45 min | Easy/Med | FALSE
2 | Phase 1: Foundations | Two Pointers | 3Sum, Container With Most Water | 60 min | Medium | FALSE
3 | Phase 1: Foundations | Two Pointers | Trapping Rain Water | 60 min | Hard | FALSE
4 | Phase 1: Foundations | Sliding Window | Longest Substring Without Repeating Characters | 45 min | Medium | FALSE
5 | Phase 1: Foundations | Sliding Window | Minimum Window Substring | 60 min | Hard | FALSE
6 | Phase 1: Foundations | Sliding Window | Subarrays with K Different Integers | 60 min | Hard | FALSE
7 | Phase 1: Foundations | Weekly Review & Mock | Timed Mock Test (2 Problems: Two Pointers / Sliding Window) | 90 min | Med/Hard | FALSE
8 | Phase 2: Persistence & Ledger | Binary Search | Search in Rotated Sorted Array | 45 min | Medium | FALSE
9 | Phase 2: Persistence & Ledger | Binary Search | Find Minimum in Rotated Sorted Array | 45 min | Medium | FALSE
10 | Phase 2: Persistence & Ledger | Binary Search | Koko Eating Bananas | 50 min | Medium | FALSE
11 | Phase 2: Persistence & Ledger | Binary Search | Capacity To Ship Packages Within D Days | 50 min | Medium | FALSE
12 | Phase 2: Persistence & Ledger | Binary Search | Median of Two Sorted Arrays | 60 min | Hard | FALSE
13 | Phase 2: Persistence & Ledger | Stacks | Min Stack, Valid Parentheses | 45 min | Easy/Med | FALSE
14 | Phase 2: Persistence & Ledger | Weekly Review & Mock | Timed Mock Test (Binary Search + Stacks) | 90 min | Med/Hard | FALSE
15 | Phase 2: Persistence & Ledger | Stacks | Evaluate Reverse Polish Notation | 45 min | Medium | FALSE
16 | Phase 2: Persistence & Ledger | Monotonic Stack | Daily Temperatures | 45 min | Medium | FALSE
17 | Phase 2: Persistence & Ledger | Monotonic Stack | Asteroid Collision | 45 min | Medium | FALSE
18 | Phase 2: Persistence & Ledger | Monotonic Stack | Largest Rectangle in Histogram | 60 min | Hard | FALSE
19 | Phase 2: Persistence & Ledger | Monotonic Stack | Online Stock Span | 45 min | Medium | FALSE
20 | Phase 2: Persistence & Ledger | Linked Lists | Reverse Linked List, Reorder List | 45 min | Easy/Med | FALSE
21 | Phase 2: Persistence & Ledger | Weekly Review & Mock | Timed Mock Test (Monotonic Stack & Linked Lists) | 90 min | Med/Hard | FALSE
22 | Phase 3: Caching & Locks | Linked Lists | Linked List Cycle I & II (Fast/Slow Pointers) | 45 min | Medium | FALSE
23 | Phase 3: Caching & Locks | Linked Lists | Merge Two Sorted Lists, Merge K Sorted Lists | 60 min | Med/Hard | FALSE
24 | Phase 3: Caching & Locks | Linked Lists | Remove Nth Node From End of List | 45 min | Medium | FALSE
25 | Phase 3: Caching & Locks | Linked Lists / Design | LRU Cache (Doubly Linked List + HashMap) | 60 min | Medium | FALSE
26 | Phase 3: Caching & Locks | Linked Lists / Design | LFU Cache (Frequency Buckets + Doubly Linked List) | 60 min | Hard | FALSE
27 | Phase 3: Caching & Locks | Trees (DFS/BFS) | Invert Binary Tree, Maximum Depth of Binary Tree | 45 min | Easy | FALSE
28 | Phase 3: Caching & Locks | Weekly Review & Mock | Timed Mock Test (LRU/LFU + Tree Traversals) | 90 min | Med/Hard | FALSE
29 | Phase 4: Kafka & Streaming | Trees (DFS/BFS) | Diameter of Binary Tree, Balanced Binary Tree | 45 min | Easy/Med | FALSE
30 | Phase 4: Kafka & Streaming | Trees (BFS) | Binary Tree Level Order Traversal | 45 min | Medium | FALSE
31 | Phase 4: Kafka & Streaming | Trees (BFS) | Binary Tree Zigzag Level Order Traversal | 45 min | Medium | FALSE
32 | Phase 4: Kafka & Streaming | Trees (DFS) | Lowest Common Ancestor of a BST & Binary Tree | 50 min | Medium | FALSE
33 | Phase 4: Kafka & Streaming | Trees (DFS) | Binary Tree Maximum Path Sum | 60 min | Hard | FALSE
34 | Phase 4: Kafka & Streaming | Trees (DFS/BFS) | Serialize and Deserialize Binary Tree | 60 min | Hard | FALSE
35 | Phase 4: Kafka & Streaming | Weekly Review & Mock | Timed Mock Test (Hard Tree Traversals & Path Sums) | 90 min | Med/Hard | FALSE
36 | Phase 5: Fintech Patterns | BST | Validate Binary Search Tree, Kth Smallest Element in BST | 50 min | Medium | FALSE
37 | Phase 5: Fintech Patterns | Graphs (BFS/DFS) | Number of Islands | 45 min | Medium | FALSE
38 | Phase 5: Fintech Patterns | Graphs (BFS/DFS) | Clone Graph | 50 min | Medium | FALSE
39 | Phase 5: Fintech Patterns | Graphs (BFS/DFS) | Pacific Atlantic Water Flow | 50 min | Medium | FALSE
40 | Phase 5: Fintech Patterns | Graphs (Topo Sort) | Course Schedule (Cycle Detection / Kahn's) | 50 min | Medium | FALSE
41 | Phase 5: Fintech Patterns | Graphs (Topo Sort) | Course Schedule II | 50 min | Medium | FALSE
42 | Phase 5: Fintech Patterns | Weekly Review & Mock | Timed Mock Test (Graphs: BFS, DFS, Topo Sort) | 90 min | Med/Hard | FALSE
43 | Phase 5: Fintech Patterns | Shortest Path | Network Delay Time (Dijkstra's Algorithm) | 50 min | Medium | FALSE
44 | Phase 5: Fintech Patterns | Shortest Path | Cheapest Flights Within K Stops (Bellman-Ford / Dijkstra) | 60 min | Medium | FALSE
45 | Phase 5: Fintech Patterns | Disjoint Sets | Number of Connected Components in Undirected Graph | 45 min | Medium | FALSE
46 | Phase 6: Enterprise Security | Disjoint Sets | Redundant Connection (Union-Find with Rank) | 50 min | Medium | FALSE
47 | Phase 6: Enterprise Security | Heaps / Priority Queue | Kth Largest Element in an Array | 45 min | Medium | FALSE
48 | Phase 6: Enterprise Security | Heaps / Priority Queue | Top K Frequent Elements | 45 min | Medium | FALSE
49 | Phase 6: Enterprise Security | Heaps / Priority Queue | Find Median from Data Stream (Two Heaps) | 60 min | Hard | FALSE
50 | Phase 6: Enterprise Security | Heaps / Priority Queue | Task Scheduler | 50 min | Medium | FALSE
51 | Phase 6: Enterprise Security | Weekly Review & Mock | Timed Mock Test (Heaps & Union-Find) | 90 min | Med/Hard | FALSE
52 | Phase 7: Full Stack UI | Dynamic Programming (1D) | Climbing Stairs, Min Cost Climbing Stairs | 45 min | Easy | FALSE
53 | Phase 7: Full Stack UI | Dynamic Programming (1D) | House Robber I & II | 50 min | Medium | FALSE
54 | Phase 7: Full Stack UI | Dynamic Programming (1D) | Longest Increasing Subsequence (LIS) | 50 min | Medium | FALSE
55 | Phase 7: Full Stack UI | Dynamic Programming (1D) | Coin Change | 50 min | Medium | FALSE
56 | Phase 7: Full Stack UI | Dynamic Programming (1D) | Maximum Subarray (Kadane's Algorithm) | 45 min | Medium | FALSE
57 | Phase 7: Full Stack UI | Dynamic Programming (1D) | Decode Ways | 50 min | Medium | FALSE
58 | Phase 7: Full Stack UI | Weekly Review & Mock | Timed Mock Test (1D Dynamic Programming) | 90 min | Med/Hard | FALSE
59 | Phase 8: Applied AI | Dynamic Programming (2D) | Unique Paths & Unique Paths II | 50 min | Medium | FALSE
60 | Phase 8: Applied AI | Dynamic Programming (2D) | Longest Common Subsequence (LCS) | 50 min | Medium | FALSE
61 | Phase 8: Applied AI | Dynamic Programming (2D) | Word Break & Word Break II | 60 min | Med/Hard | FALSE
62 | Phase 8: Applied AI | Dynamic Programming (2D) | Edit Distance | 60 min | Hard | FALSE
63 | Phase 8: Applied AI | Intervals | Merge Intervals, Insert Interval | 50 min | Medium | FALSE
64 | Phase 8: Applied AI | Intervals | Non-overlapping Intervals, Meeting Rooms II | 50 min | Medium | FALSE
65 | Phase 8: Applied AI | Weekly Review & Mock | Timed Mock Test (2D DP & Intervals) | 90 min | Med/Hard | FALSE
66 | Phase 9: Java 21 & Tuning | Backtracking | Subsets & Subsets II | 45 min | Medium | FALSE
67 | Phase 9: Java 21 & Tuning | Backtracking | Permutations & Permutations II | 50 min | Medium | FALSE
68 | Phase 9: Java 21 & Tuning | Backtracking | Combination Sum I & II | 50 min | Medium | FALSE
69 | Phase 9: Java 21 & Tuning | Backtracking | Palindrome Partitioning | 50 min | Medium | FALSE
70 | Phase 9: Java 21 & Tuning | Backtracking | Word Search | 50 min | Medium | FALSE
71 | Phase 9: Java 21 & Tuning | Backtracking | N-Queens | 60 min | Hard | FALSE
72 | Phase 9: Java 21 & Tuning | Weekly Review & Mock | Timed Mock Test (Backtracking Hard Problems) | 90 min | Med/Hard | FALSE
73 | Phase 10: DevOps & K8s | Tries | Implement Trie (Prefix Tree) | 45 min | Medium | FALSE
74 | Phase 10: DevOps & K8s | Tries | Design Add and Search Words Data Structure | 50 min | Medium | FALSE
75 | Phase 10: DevOps & K8s | Tries | Word Search II (Trie + Backtracking) | 60 min | Hard | FALSE
76 | Phase 10: DevOps & K8s | Graphs (Advanced) | Word Ladder (BFS Shortest Path) | 60 min | Hard | FALSE
77 | Phase 10: DevOps & K8s | Graphs (Advanced) | Is Graph Bipartite? | 45 min | Medium | FALSE
78 | Phase 10: DevOps & K8s | Graphs (Advanced) | Tarjan's Critical Connections in a Network (Bridges) | 60 min | Hard | FALSE
79 | Phase 10: DevOps & K8s | Weekly Review & Mock | Timed Mock Test (Tries & Advanced Graph Problems) | 90 min | Med/Hard | FALSE
80 | Phase 11: System Design | Design & Data Structures | Design Twitter (Feed, Follow, Post) | 60 min | Medium | FALSE
81 | Phase 11: System Design | Intervals & Greedy | Minimum Cost to Connect Sticks, Gas Station | 50 min | Medium | FALSE
82 | Phase 11: System Design | Shortest Path / Spanning Tree | Prim's & Kruskal's Minimum Spanning Tree | 60 min | Medium | FALSE
83 | Phase 11: System Design | Backtracking | Sudoku Solver | 60 min | Hard | FALSE
84 | Phase 11: System Design | Dynamic Programming | Burst Balloons | 60 min | Hard | FALSE
85 | Phase 11: System Design | Graph & Heaps | Alien Dictionary (Topological Sort / Verification) | 60 min | Hard | FALSE
86 | Phase 11: System Design | Weekly Review & Mock | Timed Mock Test (3 Mixed Problems - FAANG Bar) | 90 min | Med/Hard | FALSE
87 | Phase 12: Final Mocks | Speed Drill | DSA Sprint: 5 Medium Problems under 2.5 hours | 150 min | Medium | FALSE
88 | Phase 12: Final Mocks | Speed Drill | DSA Sprint: 4 Hard Problems under 3 hours | 180 min | Hard | FALSE
89 | Phase 12: Final Mocks | Weak Spot Drilling | Re-solve Previously Missed / Slow Problems | 120 min | Mixed | FALSE
90 | Phase 12: Final Mocks | Final Assessment | Full 4-Problem Company Assessment Simulation | 180 min | FAANG Bar | FALSE

## Project Implementation
Day | Phase | Project Module / Feature | The Failure / Limitation (First Seen) | The Architectural Fix (Implemented) | Status (Completed) | Code PR / Commit Link | Key Takeaways / Learnings
1 | Phase 1: Foundations & Spring Core | Base Project Setup (Spring Boot 3.x, Java 21) | Manual boilerplate POJOs without validation | Add Jakarta Validation, Java Records, verify automated schema check | FALSE
2 | Phase 1: Foundations & Spring Core | Spring Bean Lifecycle & Scopes | Singleton bean mutating internal state under concurrent requests | Refactor stateful bean to thread-safe stateless architecture / Prototype scope | FALSE
3 | Phase 1: Foundations & Spring Core | Spring AOP & Proxy Mechanics | Direct self-invocation bypasses @Transactional & @Async annotations | Inject self-proxy or extract logic into separate service layer | FALSE
4 | Phase 1: Foundations & Spring Core | Global Exception Handler & ProblemDetail | Uncaught runtime exceptions leak internal stack trace & DB error to client | Configure @ControllerAdvice with RFC 7807 ProblemDetail standard responses | FALSE
5 | Phase 1: Foundations & Spring Core | Custom Spring Boot Starter & Auto-Config | Hardcoded bean configurations prevent plug-and-play modularity | Create custom starter with @ConditionalOnProperty and spring.factories/imports | FALSE
6 | Phase 1: Foundations & Spring Core | Docker Compose: PostgreSQL & Testcontainers | Integration tests fail due to inconsistent local DB environment | Set up Testcontainers PostgreSQL for deterministic CI integration tests | FALSE
7 | Phase 1: Foundations & Spring Core | Milestone 1 Code Review & Core Architecture | Flaky and slow Spring context bootstrapping in tests | Optimize test context caching and verify clean modular starter structure | FALSE
8 | Phase 2: Data Persistence & Ledger | User, Wallet & Currency Entity Modeling | LazyInitializationException thrown outside transaction boundary | Fix entity associations, configure OpenEntityManagerInView=false cleanly | FALSE
9 | Phase 2: Data Persistence & Ledger | Double-Entry Ledger Schema Design | Single balance column susceptible to silent rounding & update drift | Implement append-only debit/credit entries with zero-sum invariant | FALSE
10 | Phase 2: Data Persistence & Ledger | Ledger Transfer Service & Batch Queries | N+1 query problem on fetching transfer history with account details | Implement JOIN FETCH, @EntityGraph and configure default_batch_fetch_size | FALSE
11 | Phase 2: Data Persistence & Ledger | Concurrency Failure in Transfer Service | Read-modify-write causes lost updates and negative wallet balances | Expose race condition using 50 concurrent threads in an integration test | FALSE
12 | Phase 2: Data Persistence & Ledger | Optimistic Locking (@Version) | Concurrent transfers fail abruptly with unhandled OptimisticLockException | Implement exponential backoff retry mechanism with Spring Retry | FALSE
13 | Phase 2: Data Persistence & Ledger | Pessimistic Locking (SELECT FOR UPDATE) | High contention leads to transaction timeouts and thread starvation | Apply PESSIMISTIC_WRITE with query hints (javax.persistence.lock.timeout) | FALSE
14 | Phase 2: Data Persistence & Ledger | Milestone 2 Concurrency Load Test | Double spending occurs under high multi-threaded transfer load | Execute Gatling load test with 500 virtual users; verify 100% balance integrity | FALSE
15 | Phase 2: Data Persistence & Ledger | HikariCP Connection Pool Tuning | Connection pool exhaustion freezes transfer API during traffic spikes | Tune maximumPoolSize, minimumIdle, and leakDetectionThreshold with metrics | FALSE
16 | Phase 2: Data Persistence & Ledger | PostgreSQL Indexing & EXPLAIN ANALYZE | Full table scan on 2M ledger rows causes p99 latency > 1200ms | Design composite index (wallet_id, created_at) to reduce query time to < 8ms | FALSE
17 | Phase 2: Data Persistence & Ledger | Table Partitioning by Transaction Date Range | Slow queries and heavy VACUUM locks on monolithic historical ledger table | Implement PostgreSQL declarative range partitioning by transaction month | FALSE
18 | Phase 2: Data Persistence & Ledger | Bulk Ledger Ingestion Script (5M Rows) | Heap OutOfMemoryError when attempting to insert 500,000 ledger records | Implement chunked batch processing with EntityManager clear() and flush() | FALSE
19 | Phase 2: Data Persistence & Ledger | Modern Java: Sealed Interfaces for Outcomes | Complex nested if-else checks and unchecked exceptions hide edge cases | Model TransferResult (Success, InsufficientFunds, NotFound, Duplicate) with sealed types | FALSE
20 | Phase 2: Data Persistence & Ledger | Modern Java: Records for DTOs & Validation | Boilerplate Lombok/POJO classes with mutable getters/setters | Convert API contracts to Java Records with compact constructor validation | FALSE
21 | Phase 2: Data Persistence & Ledger | Milestone 3 Benchmarking & Ledger Scale | Ledger queries fail SLA on large dataset | Produce EXPLAIN ANALYZE comparison report before and after optimizations | FALSE
22 | Phase 3: Caching & Distributed Locks | Redis Setup & Spring Data Redis | Cache-Aside read-modify-write causes stale cached balances | Implement proper cache invalidation and write-through policies | FALSE
23 | Phase 3: Caching & Distributed Locks | Cache Avalanche & Jittered TTL | All cache keys expire simultaneously, overwhelming PostgreSQL database | Implement randomized TTL jittering (e.g. base TTL + random 1-15%) | FALSE
24 | Phase 3: Data Persistence & Ledger | Bloom Filter for Non-Existent Wallets | Malicious requests for non-existent IDs penetrate cache straight to DB | Deploy Guava/Redis Bloom Filter to intercept invalid wallet lookups | FALSE
25 | Phase 3: Caching & Distributed Locks | Cache Stampede (Mutex Locking) | Thousands of concurrent misses on expired hot wallet key overload DB | Implement Redis distributed mutex so only one thread queries DB to rebuild cache | FALSE
26 | Phase 3: Caching & Distributed Locks | Distributed Lock via Redis SETNX + TTL | Multi-instance app deployment allows concurrent debits across servers | Implement atomic Redis SETNX with lease TTL to guard wallet transfer mutations | FALSE
27 | Phase 3: Caching & Distributed Locks | Redisson Watchdog Auto-Renewal | Long database query or GC pause causes lock TTL to expire prematurely | Configure Redisson RLock with background watchdog renewal mechanism | FALSE
28 | Phase 3: Caching & Distributed Locks | Milestone 4 Multi-Instance Load Test | Two separate application containers double-debit the same balance | Validate Redisson distributed locks prevent race conditions across 2 instances | FALSE
29 | Phase 4: Event-Driven Kafka | Kafka Cluster Setup via Docker Compose | Unpartitioned topic loses event ordering during payment updates | Define topic configuration with 6 partitions and replication factor | FALSE
30 | Phase 4: Event-Driven Kafka | Wallet Top-up & Transfer Event Producers | Dual-write bug: DB commits transaction but Kafka network call times out | Observe inconsistent states between database and published events | FALSE
31 | Phase 4: Event-Driven Kafka | Transactional Outbox Pattern (Table) | Application crash between DB commit and Kafka send causes message loss | Write domain state and outbox event within the same local DB transaction | FALSE
32 | Phase 4: Event-Driven Kafka | Outbox Event Publisher & Poller | Network partition causes publisher to resend duplicate event messages | Enable Kafka idempotent producer (enable.idempotence=true, acks=all) | FALSE
33 | Phase 4: Event-Driven Kafka | Kafka Consumer Groups & Partition Routing | Concurrent consumers process account events out of order, corrupting state | Route events using walletId as partition key to guarantee ordered processing | FALSE
34 | Phase 4: Event-Driven Kafka | Dead Letter Queue (DLQ) & Retry Topics | Malformed message triggers infinite retry loop, blocking consumer partition | Configure non-blocking retry topics with exponential backoff and DLQ | FALSE
35 | Phase 4: Event-Driven Kafka | Milestone 5 Resilient Event Pipeline | Simulated downstream consumer crash loses audit ledger events | Verify all failed events safely land in DLQ and consumer resumes cleanly | FALSE
36 | Phase 5: Fintech Design Patterns | Idempotency Interceptor (Idempotency-Key) | Network retry causes user to be charged twice for a single API call | Build Redis-backed Idempotency Filter using SHA-256 payload digest | FALSE
37 | Phase 5: Fintech Design Patterns | Double-Entry Ledger Audit Service | Discrepancies in total money supply go unnoticed without continuous audit | Write scheduled audit job verifying sum of debits equals sum of credits | FALSE
38 | Phase 5: Fintech Design Patterns | Saga Pattern: Choreography Implementation | Transfer spanning wallet and external bank leaves balance deducted on failure | Implement compensating transaction event flow to refund wallet upon failure | FALSE
39 | Phase 5: Fintech Design Patterns | Saga Pattern: Orchestrator Engine | Complex multi-step workflow states hard to track in pure choreography | Build Saga Orchestrator with persistent state machine to coordinate steps | FALSE
40 | Phase 5: Fintech Design Patterns | Resilience4j Circuit Breaker | External payment partner outage hangs HTTP threads and crashes wallet API | Wrap external gateway calls with Circuit Breaker (CLOSED/OPEN/HALF_OPEN) | FALSE
41 | Phase 5: Fintech Design Patterns | Resilience4j RateLimiter & Bulkhead | Slow external banking service exhausts Tomcat thread pool | Apply Bulkhead isolation to constrain concurrent threads per downstream vendor | FALSE
42 | Phase 5: Fintech Design Patterns | Milestone 6 Chaos Engineering Test | Inject 60% failure rate and 3-second latency on external bank mock | Verify Circuit Breaker trips to OPEN, falls back gracefully, and recovers | FALSE
43 | Phase 5: Fintech Design Patterns | Merchant Webhook Dispatcher Service | Slow merchant servers block HTTP connection threads during notification | Build asynchronous webhook queue worker pool with exponential retry backoff | FALSE
44 | Phase 5: Fintech Design Patterns | HMAC-SHA256 Webhook Signature Verification | Man-in-the-middle attacker tampers with webhook payload contents | Generate and verify X-Signature header using HMAC-SHA256 and shared secret | FALSE
45 | Phase 5: Fintech Design Patterns | Low-Level Design: Token Bucket Rate Limiter | Burst traffic floods transfer endpoints bypassing simple rate limits | Implement thread-safe Token Bucket algorithm with AtomicInteger and ReentrantLock | FALSE
46 | Phase 6: Enterprise Security | Spring Security Filter Chain & Stateless Auth | Incorrect filter chain order allows public access to secured transfer APIs | Configure explicit SecurityFilterChain with sessionManagement(STATELESS) | FALSE
47 | Phase 6: Enterprise Security | Keycloak Identity Provider Integration | Hand-rolled JWT issuing lacks token revocation and automated JWKS rotation | Integrate Keycloak as OAuth2/OpenID Connect resource server in Spring Boot | FALSE
48 | Phase 6: Enterprise Security | Role-Based Access Control (RBAC) | Regular user calls administrative ledger audit and force-reconciliation APIs | Apply @PreAuthorize('hasRole("ADMIN")') and verify 403 Forbidden enforcement | FALSE
49 | Phase 6: Enterprise Security | CORS Configuration & CSRF Protection | Frontend browser blocked by CORS policy; API vulnerable to CSRF tricks | Configure CorsConfigurationSource with strict allowed origins and CSRF tokens | FALSE
50 | Phase 6: Enterprise Security | HttpOnly Cookies vs LocalStorage Storage | XSS attack reads JWT bearer token from LocalStorage | Store refresh tokens in secure HttpOnly SameSite=Strict cookies | FALSE
51 | Phase 6: Enterprise Security | Milestone 7 Security Penetration Test | Attempt replay attacks, forged tokens, and privilege escalation | Validate all automated security test cases pass with zero security vulnerabilities | FALSE
52 | Phase 7: Full Stack UI | React Project Setup (Vite + Tailwind CSS) | Messy unstructured UI layout causes continuous prop-drilling | Structure clean feature-based modular folder architecture with Tailwind components | FALSE
53 | Phase 7: Full Stack UI | Wallet Dashboard & Balance Component | Stale balance displayed after external top-up or transfer | Integrate TanStack React Query with automated background cache invalidation | FALSE
54 | Phase 7: Full Stack UI | Transfer Money Form & Modal | User double-clicks submit button triggering duplicate API calls from UI | Implement form state validation, client-side idempotency key, and button locks | FALSE
55 | Phase 7: Full Stack UI | Paginated Ledger Transaction History Table | Rendering 1,000 ledger rows freezes browser DOM | Implement virtualized windowed list with infinite scroll pagination | FALSE
56 | Phase 7: Full Stack UI | WebSocket Live Balance & Ledger Updates | Client repeatedly polls server every 2 seconds causing high HTTP overhead | Implement Spring STOMP WebSocket broker to push real-time ledger updates | FALSE
57 | Phase 7: Full Stack UI | Axios Interceptor for Silent Token Refresh | User abruptly kicked out when access token expires after 15 minutes | Add Axios response interceptor to intercept 401 and refresh token transparently | FALSE
58 | Phase 7: Full Stack UI | Milestone 8 Full-Stack Integration Flow | Test complete money transfer journey from React frontend to PostgreSQL backend | Verify live WebSocket balance updates reflect immediately on recipient screen | FALSE
59 | Phase 8: Applied AI | Fraud Rule Engine: Velocity & Amount Checks | Bot drains account by triggering 20 transfers within 30 seconds | Implement pre-commit velocity check (max 3 transfers per minute) in filter pipeline | FALSE
60 | Phase 8: Applied AI | Geo-Location & New-Device Anomaly Flags | Login from unfamiliar country / device immediately authorizes large transfer | Flag transaction for step-up multi-factor authentication if device hash is new | FALSE
61 | Phase 8: Applied AI | PostgreSQL pgvector Extension Setup | Keyword search fails to match semantic transaction descriptions | Enable pgvector extension, create vector columns, and configure HNSW index | FALSE
62 | Phase 8: Applied AI | Spring AI Integration & LLM Client | LLM model produces hallucinated transfer amounts and balances | Configure Spring AI ChatClient with strict system prompt and temperature tuning | FALSE
63 | Phase 8: Applied AI | LLM Function / Tool-Calling Architecture | Unconstrained AI execution can trigger unauthorized debits | Wire read-only function tools (getBalance, searchTransactions) with sandboxing | FALSE
64 | Phase 8: Applied AI | RAG Pipeline over Transaction Summaries | AI bot lacks context of user's past 6 months of spending patterns | Embed ledger summaries with vector embeddings and retrieve via semantic search | FALSE
65 | Phase 8: Applied AI | Milestone 9 AI Assistant Live Demo | Ask bot: 'How much did I spend on dining last month?' | Verify LLM accurately executes tool call, queries pgvector, and returns exact sum | FALSE
66 | Phase 9: High-Throughput Java 21 | Virtual Threads (Project Loom) Integration | Tomcat thread pool hits OS limit under 10,000 concurrent I/O connections | Enable spring.threads.virtual.enabled=true to switch to lightweight virtual threads | FALSE
67 | Phase 9: High-Throughput Java 21 | Thread Pinning Detection & Fixes | Synchronized blocks pin carrier OS thread during blocking I/O calls | Run with -Djdk.tracePinnedThreads=full; replace synchronized with ReentrantLock | FALSE
68 | Phase 9: High-Throughput Java 21 | Throughput Benchmarking (Gatling) | System throughput plateaus at 800 req/sec on platform threads | Benchmark virtual threads showing 4x throughput increase on I/O-heavy ledger API | FALSE
69 | Phase 9: High-Throughput Java 21 | Memory Leak Simulation & Heap Dump | Static ledger cache retains detached entities, triggering OutOfMemoryError | Generate heap dump via jcmd; inspect dominator tree with Eclipse MAT to fix leak | FALSE
70 | Phase 9: High-Throughput Java 21 | Garbage Collection Tuning (ZGC vs G1) | G1 GC stop-the-world pauses cause p99 latency spikes above 300ms | Switch to Generational ZGC (-XX:+UseZGC) and observe sub-millisecond pauses | FALSE
71 | Phase 9: High-Throughput Java 21 | High-Performance HashMap Micro-Benchmark | Excessive hash collisions degrade lookup performance from O(1) to O(N) | Simulate hash collision attack; demonstrate treeification threshold mechanics | FALSE
72 | Phase 9: High-Throughput Java 21 | Milestone 10 Performance Sign-Off | System unstable under sustained 5,000 req/sec load | Produce final latency profiling report proving sub-50ms p99 at high throughput | FALSE
73 | Phase 10: DevOps & K8s | Multi-Stage Dockerfile Optimization | Docker image is over 850MB and takes minutes to pull during deployment | Create multi-stage Distroless Dockerfile producing a secure ~180MB image | FALSE
74 | Phase 10: DevOps & K8s | Full Stack Docker Compose Orchestration | Services crash on boot because DB or Kafka is not yet accepting connections | Add depends_on condition: service_healthy checks for PostgreSQL, Redis, Kafka | FALSE
75 | Phase 10: DevOps & K8s | GitHub Actions CI/CD Pipeline | Broken code or failing tests get merged directly into main branch | Build automated pipeline for Maven build, unit tests, SonarQube, and Docker push | FALSE
76 | Phase 10: DevOps & K8s | Jenkins Pipeline as Code (Jenkinsfile) | Enterprise bank environment requires on-premise Jenkins build pipelines | Write declarative Jenkinsfile with parallel stages, artifact archival, and test reporting | FALSE
77 | Phase 10: DevOps & K8s | Kubernetes Deployment & Service Manifests | Deploying new app version results in 10 seconds of dropped requests | Configure RollingUpdate deployment strategy with maxSurge=1, maxUnavailable=0 | FALSE
78 | Phase 10: DevOps & K8s | K8s ConfigMaps, Secrets & Health Probes | Pod accepts incoming HTTP traffic before Spring context completes initialization | Configure livenessProbe and readinessProbe targeting Spring Boot Actuator | FALSE
79 | Phase 10: DevOps & K8s | Milestone 11 Local K8s Cluster Verification | Manually kill active application pod during transfer load test | Observe Kubernetes automatically spin up healthy replica with zero dropped transfers | FALSE
80 | Phase 11: System Design | HLD: High-Level Payment Gateway Architecture | Gateway architecture has single point of failure and bottleneck | Draft complete HLD diagram: API Gateway, Tokenizer, Auth, Ledger, Settlement | FALSE
81 | Phase 11: System Design | HLD: Distributed Wallet System at Scale | Hot account ledger updates bottleneck under flash sale traffic | Design account balance sharding and asynchronous reconciliation architecture | FALSE
82 | Phase 11: System Design | HLD: Scalable Webhook Delivery Platform | Failing merchant servers overload outbound gateway HTTP workers | Design distributed webhook dispatcher with dead-letter storage and rate limiters | FALSE
83 | Phase 11: System Design | HLD: Distributed API Gateway & Rate Limiter | DDoS traffic exhausts downstream microservice cluster resources | Design distributed Token Bucket rate limiter backed by Redis cluster and Lua scripts | FALSE
84 | Phase 11: System Design | HLD: Real-Time Fraud Detection Engine | Complex rule evaluation introduces high latency to transaction authorization | Design real-time streaming pipeline using Apache Kafka and Apache Flink | FALSE
85 | Phase 11: System Design | HLD: Financial Reconciliation System | Discrepancies between internal database and bank settlement CSV files | Design batch reconciliation engine with two-way matching and discrepancy alerts | FALSE
86 | Phase 11: System Design | Milestone 12 Architecture Defense | Weak architectural justifications during technical cross-questioning | Present complete architecture walk-through defending all trade-offs and SLAs | FALSE
87 | Phase 12: Final Mocks & Polishing | Resume Metrics Extraction & Impact | Resume lists generic responsibilities without quantified production impact | Draft resume points: 'Engineered double-entry ledger reducing p99 latency to 12ms' | FALSE
88 | Phase 12: Final Mocks & Polishing | Technical Mock: Spring Boot & Concurrency | Struggling to articulate low-level transaction isolation and proxy mechanics | Complete 60-min mock interview drill on core Spring, JPA, and lock contention | FALSE
89 | Phase 12: Final Mocks & Polishing | Technical Mock: Distributed Systems & HLD | Failing to handle non-functional requirements and back-of-the-envelope math | Complete 60-min mock interview drill on Payment Gateway System Design | FALSE
90 | Phase 12: Final Mocks & Polishing | Final SDE-2 Readiness Sign-Off | Unresolved gaps or uncertainties before starting company interview loops | Full portfolio review, GitHub code polish, and official readiness certification | FALSE

## Theory & System Design
Day | Category | Core Concept / Deep-Dive Topic | Key Subtopics & Architecture Mechanics | Domain Track | Status (Completed) | Confidence (1-5) | Interview Notes / Summary
1 | Core Spring Internals | IoC Container & Bean Lifecycle | BeanFactory vs ApplicationContext; Bean instantiation phases, @PostConstruct, BeanPostProcessor | Core Framework | FALSE
2 | Core Spring Internals | Bean Scopes & Circular Dependencies | Singleton, Prototype, Request, Session; Spring 3-level cache (singletonObjects, earlySingletonObjects, singletonFactories) | Core Framework | FALSE
3 | Core Spring Internals | Spring AOP & Proxy Mechanics | JDK Dynamic Proxy (interface-based) vs CGLIB (subclassing); Proxy self-invocation trap | Core Framework | FALSE
4 | Core Spring Internals | Spring Web Request Flow | DispatcherServlet request handling, HandlerMapping, HandlerAdapter, Interceptors vs Servlet Filters | Core Framework | FALSE
5 | Core Spring Internals | Auto-Configuration Mechanics | @EnableAutoConfiguration, @Conditional annotations, spring.factories vs imports, starter structure | Core Framework | FALSE
6 | Concurrency & Memory Model | Java Memory Model (JMM) | CPU caches, store buffers, volatile keyword, happens-before relationship, instruction reordering | JVM & Multi-threading | FALSE
7 | Core Spring Internals | Weekly Review & Deep Dive | Synthesis of Spring IoC lifecycle, proxy mechanics, and framework bootstrap phases | Weekly Synthesis | FALSE
8 | Persistence & Database Internals | JPA Entity States & Dirty Checking | Transient, Managed, Detached, Removed; First-level cache, Snapshot comparison on flush | Database & ORM | FALSE
9 | Persistence & Database Internals | ACID Guarantees & Ledger Design | Atomicity, Consistency, Isolation, Durability; Accounting ledger mathematical invariants | Database & ORM | FALSE
10 | Persistence & Database Internals | Hibernate Fetch Strategies & N+1 | FetchType.LAZY vs EAGER, JOIN FETCH, EntityGraph, subselect, default_batch_fetch_size trade-offs | Database & ORM | FALSE
11 | Persistence & Database Internals | Transaction Isolation Levels | Read Uncommitted, Read Committed, Repeatable Read, Serializable; Dirty reads, Non-repeatable reads, Phantom reads | Database & ORM | FALSE
12 | Persistence & Database Internals | Concurrency Control: Locking Mechanisms | Pessimistic Locking vs Optimistic Locking; Lock modes (PESSIMISTIC_READ, PESSIMISTIC_WRITE) | Database & ORM | FALSE
13 | Persistence & Database Internals | Lock Contention & Deadlocks | Database lock escalation, lock waits, deadlock detection graphs, transaction rollback handling | Database & ORM | FALSE
14 | Concurrency & Memory Model | Synchronized Bytecode Internals | monitorenter, monitorexit; Biased Locking, Lightweight Locking (thin locks), Heavyweight Monitor locks | JVM & Multi-threading | FALSE
15 | Persistence & Database Internals | HikariCP Connection Pool Architecture | FastList, ConcurrentBag lock-free pool, connection lifecycle, pool sizing formula (connections = 2 * cores + disk_spindles) | Database & ORM | FALSE
16 | Persistence & Database Internals | PostgreSQL Indexing Internals | B-Tree internal structure, composite index column ordering rules, covering indexes (INCLUDE clause), index bloat | Database & ORM | FALSE
17 | Persistence & Database Internals | Table Partitioning Strategies | Declarative partitioning (Range, List, Hash), partition pruning by query planner, maintenance overhead | Database & ORM | FALSE
18 | Concurrency & Memory Model | CAS & Lock-Free Primitives | Compare-And-Swap hardware instructions (CMPXCHG), AtomicInteger, AtomicReference, ABA problem & AtomicStampedReference | JVM & Multi-threading | FALSE
19 | Modern Java Features | Java Sealed Classes & Pattern Matching | Sealed interfaces/classes, permits clause, record patterns, compiler-enforced exhaustiveness in switch | Java Language Deep-Dive | FALSE
20 | Modern Java Features | Java Records & Memory Layout | Record class semantics, immutability, canonical & compact constructors, shallow immutability vs deep immutability | Java Language Deep-Dive | FALSE
21 | Concurrency & Memory Model | Explicit Locks in java.util.concurrent | ReentrantLock (fair vs non-fair), ReentrantReadWriteLock, StampedLock optimistic reads | JVM & Multi-threading | FALSE
22 | Distributed Caching | Caching Architecture & Patterns | Cache-Aside, Read-Through, Write-Through, Write-Back (Write-Behind); Cache consistency guarantees | Distributed Systems | FALSE
23 | Distributed Caching | Redis Memory & Eviction Policies | Redis single-threaded event loop (epoll), memory management, eviction algorithms (noeviction, allkeys-lru, volatile-lfu) | Distributed Systems | FALSE
24 | Distributed Caching | Probabilistic Data Structures: Bloom Filters | Bit arrays, multiple hash functions, false positive probability formula, optimal size calculation, Redis Bloom module | Algorithms & Systems | FALSE
25 | Distributed Systems | Consistent Hashing & Partitioning | Consistent hash ring, virtual nodes (vnodes), handling node additions/removals, minimizing key redistribution | System Design Theory | FALSE
26 | Distributed Caching | Distributed Locking Mechanics | Single-instance Redis SETNX + PX TTL + unique token; Redlock algorithm across independent Redis masters | Distributed Systems | FALSE
27 | Concurrency & Memory Model | Thread Dumps & Diagnostic Analysis | Thread states (RUNNABLE, WAITING, TIMED_WAITING, BLOCKED), deadlocks, diagnosing thread starvation with jstack | JVM & Multi-threading | FALSE
28 | Concurrency & Memory Model | ThreadPoolExecutor Internals | CorePoolSize, MaxPoolSize, KeepAliveTime, WorkQueue types (SynchronousQueue, LinkedBlockingQueue), Rejection Policies | JVM & Multi-threading | FALSE
29 | Event-Driven & Messaging | Kafka Core Architecture | Brokers, KRaft/ZooKeeper metadata, Topics, Partitions, Segment files (.log and .index), Page cache usage | Distributed Systems | FALSE
30 | Distributed Systems | The Dual-Write Problem | Distributed consistency without 2PC, partial failure modes between database transactions and message brokers | Distributed Systems | FALSE
31 | Distributed Systems | Transactional Outbox & CDC Patterns | Outbox table polling vs Change Data Capture (Debezium reading Postgres WAL); Event Sourcing vs CRUD | Distributed Systems | FALSE
32 | Event-Driven & Messaging | Kafka Delivery Semantics | At-least-once, At-most-once, Exactly-once processing (Kafka transactions, transactional producer, read_committed) | Distributed Systems | FALSE
33 | Event-Driven & Messaging | Kafka Consumer Rebalancing | Eager rebalance vs Cooperative Sticky Assignor, heartbeat thread, max.poll.interval.ms, consumer lag monitoring | Distributed Systems | FALSE
34 | Event-Driven & Messaging | Kafka Reliability & Error Patterns | Retries, backoff topics, Dead Letter Queue (DLQ), Poison pill handling, idempotence configuration (acks=all, min.insync.replicas) | Distributed Systems | FALSE
35 | Concurrency & Memory Model | Thread Synchronization Utilities | CountDownLatch, CyclicBarrier (reusability vs one-shot), Semaphore (rate limiting/permits), Exchanger, Phaser | JVM & Multi-threading | FALSE
36 | Fintech & Reliability | Idempotency Architecture | Idempotency key semantics, IETF draft specifications, replay attack prevention, distributed lock coordination | Fintech System Design | FALSE
37 | Distributed Systems | CAP Theorem & PACELC Deep Dive | Consistency vs Availability during Partitions; Latency vs Consistency during normal operations (PACELC) | System Design Theory | FALSE
38 | Distributed Systems | Saga Pattern: Choreography vs Orchestration | Event-driven choreography vs centralized orchestrator, compensating transactions, semantic rollback challenges | System Design Theory | FALSE
39 | Distributed Systems | Distributed Transactions: 2PC vs Saga | Two-Phase Commit (Prepare, Commit) protocol, blocking coordinator vulnerability vs Saga eventual consistency | Distributed Systems | FALSE
40 | Resilience & Fault Tolerance | Circuit Breaker Pattern Mechanics | State transitions (CLOSED -> OPEN -> HALF_OPEN), sliding window metrics (count-based vs time-based), failure rate threshold | System Design Theory | FALSE
41 | Resilience & Fault Tolerance | Rate Limiting Algorithms | Token Bucket, Leaky Bucket, Fixed Window Counter, Sliding Window Log, Sliding Window Counter trade-offs | System Design Theory | FALSE
42 | Concurrency & Multi-threading | CompletableFuture & Async Pipeline | supplyAsync, thenApply, thenCompose, thenCombine; ForkJoinPool.commonPool dangers, handling async exceptions | JVM & Multi-threading | FALSE
43 | Fintech & Reliability | Webhook Delivery Architecture | Asynchronous dispatching, retry backoff with jitter, idempotent delivery, recipient verification, out-of-order webhooks | Fintech System Design | FALSE
44 | Cryptography & Security | HMAC & Cryptographic Signatures | Symmetric HMAC-SHA256 vs Asymmetric RSA/ECDSA signatures, shared secret rotation, constant-time comparison | Security Engineering | FALSE
45 | Low-Level Design (LLD) | Clean Object-Oriented Architecture | SOLID principles applied to financial systems, Strategy Pattern (fee structures), Observer Pattern (event hooks) | System Design Theory | FALSE
46 | Enterprise Security | Spring Security Core Architecture | SecurityFilterChain, SecurityContextHolder, Authentication, ProviderManager, AuthenticationProvider, Filter ordering | Security Engineering | FALSE
47 | Enterprise Security | OAuth2.0 & OpenID Connect (OIDC) | Grant types (Authorization Code + PKCE, Client Credentials), ID Token vs Access Token vs Refresh Token, JWKS verification | Security Engineering | FALSE
48 | Enterprise Security | Access Control Models | Role-Based Access Control (RBAC) vs Attribute-Based Access Control (ABAC), Spring Security Method Security (@PreAuthorize) | Security Engineering | FALSE
49 | Enterprise Security | Browser Security Model | Same-Origin Policy (SOP), Preflight OPTIONS requests, CORS headers (Access-Control-Allow-*), CSRF tokens & SameSite cookies | Security Engineering | FALSE
50 | Enterprise Security | Web Vulnerabilities & Mitigations | OWASP Top 10: SQL Injection, XSS, Broken Object Level Authorization (BOLA/IDOR), Server-Side Request Forgery (SSRF) | Security Engineering | FALSE
51 | Concurrency & Memory Model | Scoped Values & ThreadLocal Leaks | ThreadLocal pitfalls in thread pools (value leakage, memory leaks); Java 21 Scoped Values (JEP 446) immutable binding | JVM & Multi-threading | FALSE
52 | Frontend Architecture | React Virtual DOM & Reconciliation | Fiber tree architecture, diffing algorithm heuristics (keys, element types), concurrent rendering in React 18 | Full-Stack Architecture | FALSE
53 | Frontend Architecture | React Hooks Internals & Closures | useState, useEffect hook call order, stale closure trap in async callbacks, dependency array reference equality | Full-Stack Architecture | FALSE
54 | Frontend Architecture | React Performance Optimization | useMemo, useCallback, React.memo trade-offs; Profiling component re-renders with React DevTools | Full-Stack Architecture | FALSE
55 | Frontend Architecture | Client vs Server State Management | Redux Toolkit / Zustand (client state) vs TanStack Query (server cache, deduping, background sync) | Full-Stack Architecture | FALSE
56 | Real-Time Protocols | Real-Time Communication Mechanics | Short Polling vs Long Polling vs Server-Sent Events (SSE) vs WebSockets (full-duplex TCP framing) | Distributed Systems | FALSE
57 | Frontend Architecture | Token Lifecycle & Refresh Patterns | Silent token refresh, rotating refresh tokens, Axios interceptor queueing during token refresh | Security Engineering | FALSE
58 | JVM Internals | JVM Memory Layout & Architecture | Stack frames (local variables, operand stack), Metaspace (class metadata), JVM Heap (Young Gen: Eden, Survivor S0/S1; Old Gen) | JVM & Internals | FALSE
59 | Applied AI & Fraud | Financial Fraud Detection Architecture | Deterministic rule engines vs Machine Learning risk scoring; Real-time velocity counters, graph anomaly flags | Applied AI & Systems | FALSE
60 | Applied AI & Fraud | Device Fingerprinting & Identity Trust | Canvas fingerprinting, IP reputation, browser telemetry, risk-based step-up authentication triggers | Security Engineering | FALSE
61 | Applied AI & Vector DBs | Vector Embeddings & Vector Databases | High-dimensional vector representations, Distance metrics (Cosine, Euclidean, Dot Product), HNSW vs IVF indexing | Applied AI & Systems | FALSE
62 | Applied AI & LLMs | LLM Fundamentals for Backend Developers | Context window limits, tokenization, temperature/top-p sampling, System vs User prompts, prompt engineering | Applied AI & Systems | FALSE
63 | Applied AI & LLMs | LLM Function / Tool-Calling Internals | JSON Schema tool definition, model-generated tool arguments, sandbox execution, output return loop | Applied AI & Systems | FALSE
64 | Applied AI & Vector DBs | RAG (Retrieval-Augmented Generation) | Document chunking strategies, embedding generation, vector similarity search, context injection into LLM prompt | Applied AI & Systems | FALSE
65 | JVM Internals | Garbage Collection Algorithms | Generational hypothesis, Mark-Sweep-Compact, Minor GC vs Major GC vs Full GC, G1 GC (regions, card tables) vs ZGC | JVM & Internals | FALSE
66 | Java 21 & Concurrency | Virtual Threads Architecture (Project Loom) | Carrier threads (ForkJoinPool), Continuation mechanism, mounting/unmounting, why Virtual Threads don't require pooling | JVM & Multi-threading | FALSE
67 | Java 21 & Concurrency | Virtual Thread Pinning Mechanics | Synchronized blocks and native methods pinning carrier OS threads; Migration strategies to ReentrantLock | JVM & Multi-threading | FALSE
68 | Java 21 & Concurrency | Concurrency Models: Reactive vs Virtual Threads | Netty reactive event loop (WebFlux) vs Imperative Virtual Threads; Cognitive overhead vs resource efficiency | JVM & Multi-threading | FALSE
69 | JVM Internals | Memory Leak Diagnosis with Eclipse MAT | Heap dump analysis, Dominator Tree, Shallow Heap vs Retained Heap, identifying memory accumulation points | JVM & Internals | FALSE
70 | JVM Internals | ZGC & Modern Low-Latency Collectors | ZGC colored pointers, load barriers, concurrent marking/relocation, sub-millisecond GC pause targets | JVM & Internals | FALSE
71 | Collections Internals | HashMap Internal Mechanics | Hash function, bucket array, bucket index calculation (hash & (n-1)), collision resolution, treeification threshold (8), load factor (0.75) | Collections & Data Structures | FALSE
72 | Collections Internals | ConcurrentHashMap Internals | Java 7 Segment-level locks vs Java 8+ Node bin locking using CAS + synchronized; size() estimation using CounterCell | Collections & Data Structures | FALSE
73 | DevOps & Containers | Containerization & Docker Internals | Linux namespaces, cgroups, layered union filesystems, multi-stage builds, Distroless images, container security | DevOps & Cloud | FALSE
74 | DevOps & Containers | Container Networking & Orchestration | Docker bridge networks, overlay networks, container DNS resolution, healthcheck probes, volume storage | DevOps & Cloud | FALSE
75 | DevOps & Pipelines | CI/CD Pipeline Design & Best Practices | Continuous Integration vs Continuous Delivery vs Continuous Deployment, build matrices, artifact signing, test gating | DevOps & Cloud | FALSE
76 | DevOps & Pipelines | Enterprise Jenkins & Pipeline Architecture | Jenkins master-agent architecture, declarative Jenkinsfiles, shared libraries, enterprise banking compliance checks | DevOps & Cloud | FALSE
77 | DevOps & Kubernetes | Kubernetes Core Architecture | Control Plane (kube-apiserver, etcd, kube-scheduler, kube-controller-manager), Worker Nodes (kubelet, kube-proxy, CRI) | DevOps & Cloud | FALSE
78 | DevOps & Kubernetes | Kubernetes Workloads & Networking | Pods, Deployments, ReplicaSets; Services (ClusterIP, NodePort, LoadBalancer), Ingress controllers, CoreDNS | DevOps & Cloud | FALSE
79 | Distributed Systems | Database Sharding & Partitioning | Horizontal sharding, Shard keys, Resharding challenges, Virtual nodes, Cross-shard transactions & distributed joins | System Design Theory | FALSE
80 | High-Level System Design (HLD) | Payment Gateway System Architecture | End-to-end payment flow: Merchant, Gateway, Payment Processor, Card Networks, Issuing/Acquiring Banks | System Design Theory | FALSE
81 | High-Level System Design (HLD) | Distributed Wallet System Architecture | Handling hot accounts, partitioned balance ledgers, asynchronous settlement, balance caching strategies | System Design Theory | FALSE
82 | High-Level System Design (HLD) | Distributed Webhook Delivery Engine | High-throughput outbound notification engine, consumer queues, exponential backoff, rate limiting per merchant | System Design Theory | FALSE
83 | High-Level System Design (HLD) | Distributed API Gateway & Rate Limiting | API gateway responsibilities (routing, rate limiting, auth, SSL termination), Redis token bucket at scale | System Design Theory | FALSE
84 | High-Level System Design (HLD) | Real-Time Anomaly & Fraud Pipeline | Stream processing architecture (Kafka, Apache Flink), sliding event windows, stateful pattern detection | System Design Theory | FALSE
85 | High-Level System Design (HLD) | Financial Ledger & Reconciliation System | Two-way and three-way reconciliation, parsing clearing files, automated variance resolution, audit reporting | System Design Theory | FALSE
86 | JVM Internals | JVM ClassLoader Subsystem | Bootstrap, Extension/Platform, and Application ClassLoaders; Delegation model, ClassNotFoundException vs NoClassDefFoundError | JVM & Internals | FALSE
87 | Career & Interview Mastery | Quantified Resume Engineering | Transforming project tasks into production-scale impact metrics (p99 latency, throughput, concurrency guarantees) | Interview Strategy | FALSE
88 | Technical Interview Mastery | Deep-Dive Spring Boot & Concurrency | Structuring answers for SDE-2 rounds: Trade-offs, failure modes, internals, and edge-case handling | Interview Strategy | FALSE
89 | Technical Interview Mastery | System Design Interview Framework | Navigating 45-min HLD interviews: Requirements clarification, API contracts, scale estimation, failure mitigation | Interview Strategy | FALSE
90 | Final Certification | SDE-2 Interview Readiness Review | Final review of architecture portfolio, DSA problem patterns, concurrency guarantees, and mock feedback | Interview Strategy | FALSE